## Sheet1
| record_id | status | progress_high_level_accomp | risks_concerns | questions_decisions
0 | 1a | On track | None | None | None
1 | 1b | On track | none | none | none
2 | 1d | On track | None | None | None
3 | 3 | On track | rfas drafted | n/a | in associated MA charter - working on how to manage TH billing in new rate codes
4 | 4 | Minor delays | 239 of 850 beds have returned to date. All hospitals with offline beds have submitted their plans to reopen beds and have engaged with OMH in more detailed discussions. Nearly 100% of these hospitals have been submitting monthly progress reports to OMH since April 2023. | Minor delays in reopening beds due to a number of hospitals experiencing difficulty with staff recruitment. Additionally, some hospitals have exceeded the number of offline beds as reported in the original 850 due to staffing or renovation timelines. | Commissioner briefing on larger hospital system plans is scheduled for 6/1/23. We anticipate leadership direction/decision will be provided in this meeting.
5 | 5 | Minor delays | Draft bed plan is developed. Change order for largescale capital project executed, holding on other contstruction contracts/change orders until plan approval. | Delays in approval of plan are jeopardizing any year-1 start up and associated spending. Construction and renovation schedules may also be delayed until plan is approved. | Need a final 150-bed plan approval or approval of some pieces now to get staff positions allocated and filled.
6 | 6a | On track | - Jess Eber is drafting guidance on mobile crisis team transport. - Planning for state aid for rural counties is in progress; can have option to connect to this initiative. - Reviewing 9.58 trainings available. | - Some counties do not wish to do the sequential mapping exercise. - Emergency Departments are not regulated by OMH, even when part of a 9.39 designated facility. As such, any proscriptions around diversion of psychiatric transports must be done in coordination with DOH. | - Need decisions between head counsel, steering committee, and Commissioner around approving mobile crisis teams who can transport. - Regarding engaging with DOH on EDs going on psych diversion, who should reach out and what is the approach?
7 | 6bcd | On track | The draft guidance for each area has been written and shared with different OMH stakeholders for feedback. | Unclear how to roll out this guidance to A28 ERs without DOH buy-in. | Eventual, but not yet, sign off on final guidance documents. Need lower level staff input first.
8 | 11 | Minor delays | Met with OMH/OASAS Commissioners to confirm targeting strategy. Met with SAMHSA to confirm federal criteria. | RFP must be released July 1 - targeting strategy must be finalized prior. | Scheduling follow-up with both Cmmrs to finalize targeting strategy.
9 | 12 | Minor delays | Draft RFP written for Staten Island and Rockaways, Queens SOS Teams. Meetings held with subject matter experts for older adults and homeless youth. Coordination with project lead for CTI and Rural ACT to plan for locations for SOS Teams outside NYC. | Concerns have been identified by SME's around expanding age range to include youth under 18. Consent issues and lack of options outside of ACS and foster care limit interventions available. Suggestions have been to focus on transition age youth where maximum benefit can be achieved. | Age range for homeless and runaway youth services.
10 | 15 | On track | N/A | I'm unqualified | Who should do this response?
11 | 20 | On track | RFP to be finalized by May 31. Meeting with OAPSS and CBFM on June 2 to discuss outstanding questions and obtain status on B-1184. | Evaluation components require external consultant. Contracting is being explored. Funding now supports 4 teams instead of 3. Funding is from GF and CMH Federal Block Grant. | Open questions are on the agenda for June 2 meeting. Press release drafted and being routed by PIO for approvals. Nothing further needed from leadership at this time.
12 | 21 | On track | Phase II RFA was released on 5/25. | N/A | N/A
13 | 23 | Minor delays | drafting proposal | continuing eligibility discussion with DOH for HHSC | will be underspent - drafting 1x spend proposals for Y1 and Y2 - ok?
14 | 24 | On track | will release RFP after current awards are made (due 6/13) | n/a | n/a
15 | 25 | On track | CCCED RFA ready for Grants Gateway | n/a | n/a
16 | 26 | On track | Updates re new $10M ('23/'24): Received approval of concept on 5/15. A draft of the RFP is in development. Per leadership, at least one award will be set aside for a provider serving the LGBTQ youth population. Updates re original $5M ('22/'23): 5 awardees to participate in a 3-session learning collaborative during June on Supporting Teens At Risk for Suicide (STARS). Update re Evaluation for '22/'23 & '23/'24 cohorts: Meeting with OPHE & CECC on 6/5 to plan program evaluation. | - | -
17 | 27 | On track | Draft RFA complete, meeting with internal OPHI leadership today for feedback on edits provided. | no concerns | none at this time
18 | 29 | On track | Comments for State Aid Letter and Contract Allocations finalized. Review of eligible fund codes and programs complete. State Aid Letter allocations underway and aniticipated completion by June 9 for July SAL issuance and payment. Contract allocations will begin after SAL allocations complete. | Will want to issue contract amendments with both COLA and Residential Stipend increases. Issuing amendments may be delayed if DOB does not approve Residential stipend increases in a timely manner. | None at this time
19 | 30 | On track | B-1184 seeking approval of proposed Stipend increases is at DOB for review and approval since 5/23. | Time for DOB approval is only risk at this time. CBFM is following up daily on status with DOB. | None at this time.
20 | 33 | On track | - 890+ participants attended 4 virtual sessions in February & March 2023 - 835 participants attended 35 in-person sessions in March & April, covering 18 locations throughout the state - Guidehouse completed the qualitative analysis and it was distributed internally to MHI responsible leads - Next step is to present results to county DCSs in 5 regional meetings - Public-facing version is in progress. | - Results of qualitative analysis are lengthy and takes time for responsible leads to read and absorb; Excel version is in progress | - When a public-facing version draft is ready, we will need steering committee's approval to post on our website and circulate outside of OMH
21 | 34 | On track | data gathered on beds per region | n/a | What $ amount for RTF capital? Any startup?